

**Final Year Project Plan**

SCSE23-0501 – Object Detection on a Mobile Device

**Dion Toh Siyong U2021674D**

Academic Year 2023-24

School of Computer Science & Engineering

Nanyang Technological University, Singapore

Submitted to—

Dr Deepu Rajan

School of Computer Science & Engineering

Nanyang Technological University, Singapore

## Contents

[Background 3](#_Toc144634670)

[Objective 3](#_Toc144634671)

[Timeline 3](#_Toc144634672)

[Gantt Chart 4](#_Toc144634673)

[Work Breakdown Structure 5](#_Toc144634674)

# Background

In an age dominated by the rapid evolution of deep fake technology, the urgent need to combat the spread of digitally manipulated content has never been more pressing. I will utilise Detectron2, a state-of-the-art object detection framework, to train a detection model aimed at efficiently identifying deep fake content. Current solutions for detecting deep fakes are resource-intensive, limiting accessibility for the average user and resource-constrained environments. This project aims to solve this problem by training a lightweight model, optimised to be able to be deployed on widely available hardware such as smartphones.

# Objective

The primary aim of this project is to create an efficient deep learning framework tailored for object detection, specifically designed for mobile device deployment. Our approach leverages Detectron2, an advanced object detection framework developed by Facebook AI Research, known for its cutting-edge performance in this domain. The end goal is for the object detection model to be able to help identify deep fake content.

# Timeline

The project will be carried over two semesters, including the winter break of December. The project has been divided into four sub-parts:

1. **Project Planning** 
   1. Project Scope
   2. Requirements Elicitation
   3. Literature Review

1. **Machine Learning**
   1. Data Collection
   2. Data Preparation
   3. Model Training
   4. Accuracy Testing
   5. Model Optimisation and Refinement

1. **Mobile App**
   1. Mobile Application Development
   2. Deployment of ML model and Testing

1. **Project Deliverables** 
   1. Interim FYP Report
   2. Final FYP Report
   3. Amended Final FYP Report
   4. Completed Mobile App
   5. Oral Presentation

# Gantt Chart

A graph with multiple colored squares

Description automatically generated with medium confidence

**Figure 1:** Gantt chart for the project. A task gap is present in November to account for the semester end examinations.

# Work Breakdown Structure

|  |  |  |  |
| --- | --- | --- | --- |
| Category | Name | Estimated Start Date(MM/DD/YY) | Estimated End Date(MM/DD/YY) |
| **Planning** | Define Project Scope | 8/10/23 | 8/20/23 |
|  | Requirements Elicitation | 8/10/23 | 9/6/23 |
|  | Literature Review | 8/10/23 | 9/20/23 |
| **Implementation (Model Training)** | Data Collection & Preparation | 9/21/23 | 1/15/24 |
|  | Model Training | 10/6/23 | 11/10/23 |
|  | Model Refinement | 11/29/23 | 1/20/24 |
|  | Model Deployment | 12/20/23 | 1/2/24 |
| **Implementation (Mobile Deployment)** | Application Development | 11/29/23 | 12/20/23 |
|  | Backend Development | 12/20/23 | 1/2/24 |
|  | Self Testing & Bug Fixing | 1/2/24 | 1/20/24 |
| **Deliverables** | Interim FYP Report | 12/6/23 | 1/29/24 |
|  | Final FYP Report | 1/29/24 | 3/25/24 |
|  | Amended FYP Report | 3/25/24 | 4/19/24 |
|  | Oral Presentation | 4/19/24 | 5/15/24 |